## Project Timeline
S&B Landscaping Milestone Review COSC412
Line chart that plots each milestone on the corresponding timeframe is in this cell.
Project Milestones
Date | Milestone | Assigned To | Position | Baseline | Complete or not? [Y/N]
2021-01-26 | Announcement of Individual Project | Brandon | 20 | 0 | [N/A] Milestones created for project.
2021-02-01 | Planning ideas for individual project | Brandon | 10 | 0 | [Y] This milestone was completed. All ideas were planned and deemed what would work best.
2021-02-05 | Propose Individual Project Idea to Professor Broadwater | Brandon | -5 | 0 | [Y] Milestone was completed when topic was approved.
2021-02-19 | Complete Use Case Diagram | Brandon | 5 | 0 | [Y] Milestone was completed, but can change if requirements change as site is developed.
2021-02-19 | Complete SPMP Individual | Brandon | -15 | 0 | [Y] Milestone was completed, but can change if requirements change as site is developed.
2021-03-28 | Meet with Professor Broadwater 9:30pm | Brandon | 15 | 0 | [Y] Milestone was complete after the meeting was finished on 3/28.
2021-04-02 | Purchase domain (sblandscaping.biz) | Brandon | -5 | 0 | [Y] Milestone was complete when domain was purchased from Namecheap.
2021-05-01 | Design main site features and layout features | Brandon | 15 | 0 | [Y] Milestone was complete when main was designd from Namecheap.
2021-05-01 | Install needed plugins for best functionality | Brandon | -20 | 0 | [Y&N] Main plug ins have been established, but site is not fully complete yet. There is possibility of new plug ins to be added.
2021-05-01 | Test funcationality of site | Brandon | 25 | 0 | [Y&N] Site is being tested as new features are added but site isn't complete yet.
2021-05-01 | Present to small audidence for last minute feedback | Brandon | -15 | 0 | [N] Site hasn't been completed and presented to audience for feedback yet.
2021-05-09 | Implement given feedback from audience | Brandon | 10 | 0 | [N] No feedback has been given yet.
2021-05-11 | Submit and Present project to class and Professor Broadwater | Brandon | 5 | 0 | [N] Project hasn't been submitted yet or presented.